## ProductBackLog
Project Name: A Centralized Platfrom for Educational and Career Opportunities Group Members:Kaan DÖNMEZ ,Hilal Seray ORTAN,Baran Deniz AYDIN,Salih Batuhan ŞENER,Doruk YAŞAR,Selin TAY,Ömer ŞEN
# | Product BackLog
1 | Database Design & Planning
2 | User Registration and Authentication
3 | Search & Filter Functionality
4 | AI-Based Recommendation Engine
5 | Personalized Feed System
6 | Notification System
7 | Review & Feedback System
8 | Interview & Video Interaction System
9 | Deadline Reminder System
10 | Duplicate Application Prevention System
11 | Performance & Response Time Optimization
12 | Multi-Language Support
13 | Basic Security
14 | Advanced Security & Data Protection
15 | Concurrent User Testing
16 | User Profile Management
17 | Application and Tryout Tracking System
18 | Favorties / Bookmark Sytem
19 | Role and Access Management
20 | Opportunity Data Setup
21 | Analytics & Reporting System

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Scrum Master(H.O), Product Owner (K.D.) | Database Design & Planning | In Progress | High | 2026-02-16 | 2026-02-19 | 4 | A robust database is the central repository that stores and organizes all application data.
Developer (S.T.) | Opportunity Data Setup | Ready to Start | High | 2026-02-20 | 2026-02-22 | 3 | Creates the basic database schema for opportunities and injects initial data to make the search function testable.
Developer (D.Y.) | User Registration and Authentication | Ready to Start | High | 2026-02-21 | 2026-02-23 | 3 | Basic sign-up/login system. Critical for user access to the platform.
Developer (O.S) | Role and Access Management | Ready to Start | High | 2/24/2026 | 2026-02-25 | 2 | Defines specific user roles (Student, Employer, Admin) to control platform access and features.
Developer (S.B.Ş.) | Basic Security | Ready to Start | High | 2026-02-24 | 2026-02-25 | 2 | The system ensures secure authentication and protects user data through fundamental security mechanisms.
10
BACKLOG
As a user, I want to register with my email address and password, so that I can access the platform and discover opportunities.
STATUS: Ready to Start
S.T
As a developer, I want to design the database schema, so that all application data is stored in a structured and scalable way.
STATUS: In Progress
D.Y
As a user, I want to select whether I am a student or an employer during registration, so that I can access the features relevant to my needs.
STATUS: Ready to start
As a developer, I want to set up the opportunity data structure and add initial mock data so that the search and filter functionalities can be tested.
STATUS : Ready to start
O.S.
O.S

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer (S.T) | Search & Filter Functionality | Ready to Start | Medium | 2026-02-26 | 2026-03-01 | 4 | Users can search and filter opportunities by location, date, and required skills to find the most relevant ones quickly.
Developer (K.D) | Personalized Feed System | In progress | High | 2026-02-28 | 2026-03-03 | 4 | Provides relevant opportunities based on user profile to enhance user engagement.
Developer (H.O) | Application and Tryout Tracking System | Not Started | High | 2026-03-01 | 2026-03-03 | 3 | An interface for users to track their incoming and past applications.
Developer (D.Y) | Favorties / Bookmark Sytem | Not Started | Medium | 2026-03-02 | 2026-03-03 | 2 | Users can save and easily access preferred opportunities for future reference.
Developer (B.D.A) | User Profile Management | Not Started | Medium | 2026-04-03 | 2026-03-06 | 3 | Users can create and update their personal information, preferences, and application details.
11
BACKLOG
As a developer, I want to validate opportunity data so that users receive accurate and reliable information.
STATUS: Not Started
As a developer, I want to implement the opportunity browsing module so that users can easily access and view available opportunities.
STATUS: In progess
As a user, I want to search and filter opportunities by location, date, and required skills, so that I can quickly find the most relevant opportunities for me.
STATUS : Ready to Start
S.T.
S.T.
As a customer, I want to see personalized opportunities based on my profile so that I can quickly find relevant options.
Status: In progress

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer (S.B.Ş) | AI-Based Recommendation Engine | Not Started | High | 2026-07-03 | 2026-11-03 | 5 | System to provide suggestions based on qualification and interests.
Developer (S.T) | Notification System | Not Started | High | 2026-03-12 | 2026-03-14 | 3 | Keeps users informed about new opportunities and important updates.
Developer (O.S) | Deadline Reminder System | Not Started | High | 3/13/2026 | 3/14/2026 | 2 | The system checks opportunity links daily and removes expired or inactive opportunities automatically.
Developer (K.D) | Duplicate Application Prevention | Not Started | Medium | 3/15/2026 | 3/16/2026 | 2 | The system prevents users from applying to events that occur at the same date and time.
Developer (H.O) | Analytics & Reporting System | Not Started | Medium | 3/16/2026 | 3/18/2026 | 3 | The system collects and analyzes user activity and opportunity data to generate useful insights and reports.
12
BACKLOG
As a user, I want the system to remove expired opportunities automatically, so that I only see active opportunities.
Status: Not Started
As a customer, I want to save opportunities and receive deadline reminders so that I do not miss important applications.
STATUS: Ready to start
As a user, I want the system to prevent applying to events at the same time, so that I do not have schedule conflicts. Status: Not Started
S.B.Ş
S.B.Ş

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer (S.T) | Review & Feedback System | Not Started | Medium | 2026-03-19 | 2026-03-21 | 3 | Ensure proper algorithm to prioritizing showing relevant feedbacks.
Developer (H.O) | Interview & Video Interaction System | Not Started | High | 3/20/2026 | 3/23/2026 | 4 | A system that enables real-time video interviews and messaging.
Developer (K.D) | Performance & Response Time Optimization | Not Started | Medium | 3/24/2026 | 3/26/2026 | 3 | Improves system performance to meet response time requirements.
Developer (B.D.A) | Multi-Language Support | Not Started | Low | 2026-03-25 | 2026-03-26 | 2 | Translate the entire application to decided languages using API's.
Developer (S.B.Ş) | Advanced Security & Data Protection | Not Started | High | 2026-03-27 | 2026-03-30 | 4 | Integrate proper data and privacy protection measures.
Developer (D.Y) | Concurrent User Testing | Not Started | High | 2026-03-31 | 2026-04-02 | 3 | Test system performance under multiple concurrent users.
14
BACKLOG
As a developer, I want to protect user data using security methods, so that user information stays safe and secure.
STATUS: Not Started
As a user, I want the system to be easy to use for everyone so that all users can access and understand it without difficulty.
STATUS: Not Started
S.T
D.Y

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here